## Sheet1
Gantt Chart for project
Task ID | Task Name | Start Date | Days to complete
1 | ER Diagram | 2021-11-17 | 14
2 | DB Schema | 2021-11-24 | 14
3 | Front End/UI | 2021-11-24 | 35
4 | Database Interaction | 2021-12-01 | 30
5 | Final Report | 2021-12-08 | 21